## Sheet1
Budget Plan: Urban Residential Redesign for Sustainable Living Berta & Richard Kuhnel | [8 empty] | 908 Oak St, Sandpoint, ID 83864
Phase 1
CASHFLOW | planned | planned | planned | planned | planned | planned | planned | planned | planned | planned | planned | planned | TOTALS | AVERAGE
JOINT | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | March | April
Funds In
Reserve | MAY: 3300 | 3300 | 275
RICHARD | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 500 | 500 | 500 | 500 | 500 | 4950 | 412.5
BERTA | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 500 | 500 | 500 | 500 | 500 | 4950 | 412.5
Classes | OCT: 400; JAN: 400; April: 400 | 1200 | 100
Gifts | OCT: 5000; NOV: 5000; March: 5000; April: 3000 | 18000 | 1500
Other | [12 empty] | 0 | 0
Total | 4000 | 700 | 700 | 700 | 700 | 6100 | 5700 | 1000 | 1400 | 1000 | 6000 | 4400 | 32400
Expenses
Labor | JUN: 2000; JUL: 2000 | 4000 | 333.3333
Permits | JUN: 575 | 575 | 47.9167
Events | JUN: 100 | 100 | 8.3333
Equipment - purchase | JUN: 1000 | 1000 | 83.3333
Equipment - rent | JUN: 500 | 500 | 41.6667
Landscaping | MAY: 150; JUN: 1500 | 1650 | 137.5
Sewage pipe replacm. | JUN: 150 | 150 | 12.5
Water catchment | JUN: 100; JUL: 500; AUG: 2500 | 3100 | 258.3333
Irrigation | JUN: 250 | 250 | 20.8333
Fencing | JUN: 250 | 250 | 20.8333
Finishes | [12 empty] | 0 | 0
Patio | JUL: 500 | 500 | 41.6667
Deck & Porch | JUL: 5000 | 5000 | 416.6667
Sidewalk & Driveway | JUN: 2000 | 2000 | 166.6667
Greenhouse | AUG: 3000; SEP: 2000 | 5000 | 416.6667
Cob bench | AUG: 1000 | 1000 | 83.3333
Solar | AUG: 2500; SEP: 2000 | 4500 | 375
Misc. | JUN: 166; AUG: 100 | 266 | 22.1667
TOTAL EXP. | 150 | 8591 | 8000 | 9100 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29841 | 3730.125
Over/Under | 3850 | -7891 | -7300 | -8400 | -3300 | 6100 | 5700 | 1000 | 1400 | 1000 | 6000 | 4400
Beginning | 0 | 3850 | 5959 | 4659 | 2259 | 959 | 1059 | 759 | 1759 | 3159 | 159 | 1159
Loan received | JUN: 10000; JUL: 6000; AUG: 6000; SEP: 2000 | 24000
Loan paid back | OCT: 6000; NOV: 6000; FEB: 4000; March: 5000; April: 3000 | 24000
Ending Bank | 3850 | 5959 | 4659 | 2259 | 959 | 1059 | 759 | 1759 | 3159 | 159 | 1159 | 2559