## Sheet1
Budget Plan: Urban Residential Redesign for Sustainable Living Berta & Richard Kuhnel | [10 empty] | 908 Oak St, Sandpoint, ID 83864
Phase 1
CASHFLOW | actual | planned | actual | planned | planned | planned | planned | planned | planned | planned | planned | planned | planned | planned | TOTALS | AVERAGE
JOINT | MAY | MAY | JUN | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | March | April
Funds In
Reserve | MAY: 3300; JUN: 1650 | 1650 | 137.5
RICHARD |  | 350 | 680 | 350 | 350 | 350 | 350 | 350 | 350 | 500 | 500 | 500 | 500 | 500 | 4930 | 410.8333
BERTA |  | 350 | 680 | 350 | 350 | 350 | 350 | 350 | 350 | 500 | 500 | 500 | 500 | 500 | 4930 | 410.8333
Classes | OCT: 400; JAN: 400; April: 400 | 1200 | 100
Gifts | OCT: 5000; NOV: 5000; March: 5000; April: 3000 | 18000 | 1500
Other | [14 empty] | 0 | 0
Total | 0 | 4000 | 3010 | 700 | 700 | 700 | 700 | 6100 | 5700 | 1000 | 1400 | 1000 | 6000 | 4400 | 30710
Expenses
Labor | JUN: 4726.59; JUN: 2000; JUL: 2000 | 6726.59 | 560.5492
Permits | JUN: 575 | 0 | 0
Events | JUN: 100 | 0 | 0
Equipment - purchase | JUN: 225.73; JUN: 1000 | 225.73 | 18.8108
Equipment - rent | JUN: 500 | 0 | 0
Garden Extension | MAY: 150; JUN: 53.8; JUN: 1500 | 53.8 | 4.4833
Sewage pipe replacm. | JUN: 134; JUN: 150 | 134 | 11.1667
Water catchment | JUN: 100; JUL: 500; AUG: 2500 | 3000 | 250
Irrigation | JUN: 250 | 0 | 0
Fencing | JUN: 250 | 0 | 0
Finishes | [14 empty] | 0 | 0
Patio | JUL: 500 | 500 | 41.6667
Deck & Porch | JUL: 5000 | 5000 | 416.6667
Sidewalk & Driveway | JUN: 1096.68; JUN: 2000 | 1096.68 | 91.39
Shed Extension | JUN: 92.32
Greenhouse / Porch | AUG: 3000; SEP: 2000 | 5000 | 416.6667
Cob bench | AUG: 1000 | 1000 | 83.3333
Solar | AUG: 2500; SEP: 2000 | 4500 | 375
Trailer | JUN: 177.66
Misc. | JUN: 14; JUN: 166; AUG: 100 | 114 | 9.5
TOTAL EXP. | 0 | 150 | 6520.78 | 8591 | 8000 | 9100 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27620.78 | 3452.5975
Over/Under | 0 | 3850 | -3510.78 | -7891 | -7300 | -8400 | -3300 | 6100 | 5700 | 1000 | 1400 | 1000 | 6000 | 4400
Beginning | 0 | 0 | 0 | 0 | 11489.22 | 5189.22 | 2789.22 | 1489.22 | 1589.22 | 1289.22 | 2289.22 | 3689.22 | 689.22 | 1689.22
Loan received | JUN: 15000; JUN: 15000; JUL: 1000; AUG: 6000; SEP: 2000 | 24000
Loan paid back | OCT: 6000; NOV: 6000; FEB: 4000; March: 5000; April: 3000 | 24000
Ending Bank | 0 | 3850 | 11489.22 | 7109 | 5189.22 | 2789.22 | 1489.22 | 1589.22 | 1289.22 | 2289.22 | 3689.22 | 689.22 | 1689.22 | 3089.22
-1291