## Project Budget and Cashflow
Budget Plan: Urban Residential Redesign for Sustainable Living Berta & Richard Kuhnel | [11 empty] | 908 Oak St, Sandpoint, ID 83864
Phase 1
CASHFLOW | actual | planned | actual | planned | actual | planned | planned | planned | planned | planned | planned | planned | planned | planned | planned | Current | Current | TOTAL | TOTALS
JOINT | MAY | MAY | JUN | JUN | JUL | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | March | April | actual | planned |  | planned
Funds In
Reserve |  | 3300 | 1650 | [12 empty] | 1650 | 3300 | 1650 | 3300
RICHARD |  | 350 | 680 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 500 | 500 | 500 | 500 | 500 | 1030 | 1050 | 4930 | 4950
BERTA |  | 350 | 680 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 500 | 500 | 500 | 500 | 500 | 1030 | 1050 | 4930 | 4950
Classes | [8 empty] | 400 |  |  | 400 |  |  | 400 | 0 | 0 | 1200 | 1200
Gifts | [8 empty] | 5000 | 5000 |  |  |  | 5000 | 3000 | 0 | 0 | 18000 | 18000
Other | [15 empty] | 0 | 0 | 0 | 0
Total | 0 | 4000 | 3010 | 700 | 700 | 700 | 700 | 700 | 6100 | 5700 | 1000 | 1400 | 1000 | 6000 | 4400 | 3710 | 5400 | 30710 | 32400
Expenses
Labor |  |  | 4726.59 | 2000 | 3015.94 | 2000 | [9 empty] | 7742.53 | 4000 | 7742.53 | 4000
Extra Groceries, help |  |  |  |  | 580.8 | [10 empty] | 580.8 | 0 | 580.8 | 0
Permits |  |  |  | 575 | 183.56 | [10 empty] | 183.56 | 575 | 183.56 | 575
Events |  |  |  | 100 | [11 empty] | 0 | 100 | 0 | 100
Equipment - purchase |  |  | 225.73 | 1000 | 205.13 | [10 empty] | 430.86 | 1000 | 430.86 | 1000
Equipment - rent |  |  |  | 500 | 401.07 | [10 empty] | 401.07 | 500 | 401.07 | 500
Transportation |  |  |  |  | 39.1 | [10 empty] | 39.1 | 0 | 39.1 | 0
Neighborhood meeting |  |  |  |  | 68.92 | [10 empty] | 68.92 | 0 | 68.92 | 0
Garden Extension |  | 150 | 53.8 | 1500 | 20 | [10 empty] | 73.8 | 1650 | 73.8 | 1650
Sewage pipe replacm. |  |  | 134 | 150 | [11 empty] | 134 | 150 | 134 | 150
West Foot Path |  |  |  |  | 165 | [10 empty] | 165 | 0 | 165 | 0
Water catchment |  |  |  | 100 |  | 500 | 2500 | [8 empty] | 0 | 600 | 2500 | 3100
Irrigation |  |  |  | 250 | [11 empty] | 0 | 250 | 0 | 250
Fencing |  |  |  | 250 | [11 empty] | 0 | 250 | 0 | 250
Finishes | [15 empty] | 0 | 0 | 0 | 0
Patio | [5 empty] | 500 | [9 empty] | 0 | 500 | 0 | 500
Deck & Porch | [5 empty] | 5000 | [9 empty] | 0 | 5000 | 0 | 5000
Sidewalk & Driveway |  |  | 1096.68 | 2000 | 414.8 | [10 empty] | 1511.48 | 2000 | 1511.48 | 2000
Shed Extension |  |  | 92.32 | [12 empty] | 92.32 | 0 | 92.32 | 0
Greenhouse / Porch |  |  |  |  | 678.98 |  | 3000 | 2000 | [7 empty] | 678.98 | 0 | 5678.98 | 5000
Cob bench | [6 empty] | 1000 | [8 empty] | 0 | 0 | 1000 | 1000
Solar | [6 empty] | 2500 | 2000 | [7 empty] | 0 | 0 | 4500 | 4500
Trailer |  |  | 177.66 | [12 empty] | 177.66 | 0 | 177.66 | 0
Misc. |  |  | 14 | 166 | -14.11 |  | 100 | [8 empty] | -0.11 | 166 | 99.89 | 266
TOTAL EXP. | 0 | 150 | 6520.78 | 8591 | 5759.19 | 8000 | 9100 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12279.97 | 16741 | 25379.97 | 29841
Over/Under | 0 | 3850 | -3510.78 | -7891 | -5059.19 | -7300 | -8400 | -3300 | 6100 | 5700 | 1000 | 1400 | 1000 | 6000 | 4400
Beginning | 0 | 0 | 0 | 0 | 11489.22 | 11489.22 | 6430.03 | 4030.03 | 2730.03 | 2830.03 | 2530.03 | 3530.03 | 4930.03 | 1930.03 | 2930.03
Loan received |  |  | 15000 | 15000 | 1285.95 | 1000 | 6000 | 2000
Loan paid back |  |  |  |  | 1285.95 |  |  |  | 6000 | 6000 |  |  | 4000 | 5000 | 3000
Ending Bank | 0 | 3850 | 11489.22 | 7109 | 6430.03 | 5189.22 | 4030.03 | 2730.03 | 2830.03 | 2530.03 | 3530.03 | 4930.03 | 1930.03 | 2930.03 | 4330.03
Note on Q3: Only the up to date total numbers
Note on R3: Only what was planned up to date totals
Note on S3: The up to date actual numbers and the future planned numbers
Note on T3: Planned